## Version History
Version History
Project Name | Pickaboo
Created By | Afrida Rahman
Version Number | 1
Creation Date | 2023-11-22
Version Updated Date | 2023-11-22

## Test Plan
Test Plan link: Pickaboo

## Test Scenario
Project Name | Pickaboo
Reference Document | FRS
Created By | Afrida Rahman
Creation Date | 2023-11-22
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 | FRS | Validate the URL in different browsers | P0 | 1
TS_002 | FRS | Validate the "Register" functionality | P1 | 29
TS_003 | FRS | Validate the "Login" functionality | P0 | 10

## Test Case
Product Name | Pickaboo | [6 empty] | TEST CASE
Module Name | Register and Sing In | TC Start Date | 2023-11-22 | TC Execution Start Date | 2023-11-25 |  |  | PASS | 32
Epic |  | TC End Date | 2023-11-24 | TC Execution End Date | 2023-11-27 |  |  | FAIL | 8
Developer Name |  | Test Case Developed By | Afrida Rahman | Browser (tested) | Yes |  |  | Not Executed | 0
Test Executed by |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | Yes |  |  | Out of Scope | 0
[8 empty] | TOTAL | 40
#SL | Module | Features | Type of Testing | Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  |  | Browser Compatibliti Testing | Checking by running in different browsers | Should run in different | Found as per expectation | Chrome, Internet Explorer, Mozilla Firefox, Microsoft Edge, Opera Mini | 1. Goto different browsers 2. Search 'Pickaboo' 3. Goto the website |  |  | Passed
2 | User Management | Sign up / Register | UI Testing | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per requirement | Found as per expectation | N/A | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Check the font, text color and style |  |  | Passed
4 |  |  |  | Checking alignment of the fields | Proper alignment of the fiels should be present | Found as per expectation | N/A | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Check the alignment of the fields |  |  | Passed
5 |  |  | Functional Testing | Keeping mandatory fields blank | Should be as per requirement | Should not allow user to register and give pop an error message | N/A | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Keep mandatory field blank |  |  | Passed
6 |  |  |  | Checking firstname and lastname field is case insensitive | Should accept the provider input | Found as per expectation | AFFrridA, afRRiiDDa | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Input AFFrridA and afRRiiDDa as firstname and lastname |  |  | Passed
7 |  |  |  | Entering blank at first position in firstname and lastname field | Should not accept the provided input | Not found as per expectation | Afrida, Rahman | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Input space in first position on firstname and lastname | First Blank position error |  | Failed
8 |  |  |  | Entering blank at last position in firstname and lastname field | Should not accept the provided input | Not found as per expectation | Afrida , Rahman | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Input space in first position on firstname and lastname | Last Blank position error |  | Failed
9 |  |  |  | Checking alert message for all mandatory fields | Should pop an error message | Not found as per expectation | N/A | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Keeping blank in each field and checking repeatedly |  |  | Failed
10 |  |  |  | Inputing firstname and lastname with special characters | Should not accept the provided input | Not found as per expectation | %#@, )(*%#@^* | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Input special character in first and last position on firstname and lastname | Special character error |  | Failed
11 |  |  |  | Inputing firstname and lastname with numbers | Should not accept the provided input | Not found as per expectation | 0123456789, 9876543210 | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Input numbers in first and last position on firstname and lastname | Number error |  | Failed
12 |  |  |  | Inputing firstname and lastname with decimal numbers | Should not accept the provided input | Not found as per expectation | 12345.6789, 9876.5432 | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Input decimal numbers in first and last position on firstname and lastname | Decimal number error |  | Failed
13 |  |  |  | Inputing firstname and lastname with alphabets | Should accept the provided input | Found as per expectation | Afrida Rahman | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Input alphabets in first and last position on firstname and lastname |  |  | Passed
14 |  |  |  | Entiring comma between alphabets for firstname and lastname | Should not accept the provided input | Not found as per expectation | Afri,da Rah,man | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Input alphabets in first and last position on firstname and lastname | Comma in firstname and lastname |  | Failed
15 |  |  |  | Checking by inputing invalid mobile number | Should not accept the provided input and display an error message | Not found as per expectation | 17788448 | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Input invalid mobile number in Mobile Number field |  |  | Failed
16 |  |  |  | Check the sending OTP number | Should send an OTP number to the valid phone number | Found as per expectation | 2312 | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Input all required information and on the provided number an OTP sent |  |  | Passed
17 |  |  |  | Validating an email id can only be used one time | Should not allow user to register and display a pop message | Found as per expectation |  | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Input an used mail on the email field |  |  | Passed
18 |  |  |  | Checking by inputing invalid email format | Should not accept the provided input and display an error message | Found as per expectation | abc@xyz | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Fill the email address with invalid email address format |  |  | Passed
19 |  |  |  | Checking by inputing valid email format | Should accept the provided input | Found as per expectation | afridaurmi@gmail.com | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Fill the email address with valid email address format |  |  | Passed
20 |  |  |  | Checking the password field values are masked | Should be masked | Found as per expectation | afrida123456 | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Enter password and confirm password |  |  | Passed
21 |  |  |  | Inputing invalid combinations of characters in password and confirm password field | Should not allow user to register and display an error message | Found as per expectation | afrida123456 | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Enter invalid combinations of character in password and confirm password |  |  | Passed
22 |  |  |  | Inputing weak password length | Should allow user to register | Found as per expectation | asdfgh | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Enter weak password length in password and confirm password |  |  | Passed
23 |  |  |  | Inputing medium password length | Should allow user to register | Found as per expectation | asdfgh%123 | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Enter medium password length in password and confirm password |  |  | Passed
24 |  |  |  | Inputing strong password length | Should allow user to register | Found as per expectation | afrida@09876 | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Enter strong password length in password and confirm password |  |  | Passed
25 |  |  |  | Inputing different data for password and confirm password | Should not allow user to register and display a pop message | Found as per expectation | Password: afrida@09876 Confirm Password: afrida@12345 | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Enter different values in password and confirm password |  |  | Passed
26 |  |  |  | Checking "Sign in with Google" | Should allow user to register | Found as per expectation | Click on "Sign in with Google" | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Click on "Sign in with Google" |  |  | Passed
27 |  |  |  | Checkinf "Sign in with Facebook" | Should allow user to register | Found as per expectation | Click on "Sign in with Facebook" | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Click on "Sign in with Facebook" |  |  | Passed
28 |  |  | Usability Testing | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | afrida09876 | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Copy paste text in every field |  |  | Passed
29 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Enter tab in every field |  |  | Passed
30 |  |  |  | Checking keyboard enter button functionality | Should switch to another fiels | Functioning successfully | Input enter in every field | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Enter enter in every field |  |  | Passed
31 |  | Sign in / Login | Functional Testing | Verify all login-related elements and fields are present on the login page. | Should be present the mandatory field | Found as per expectation | N/A | 1. Goto the url "https://www.pickaboo.com/" 2. Click on login button at the right corner 3. Check all login related information are present on login page |  |  | Passed
32 |  |  |  | Keep email and password field blank | Should not allow user to login and display an error message | Found as per expectation | N/A | 1. Goto the url "https://www.pickaboo.com/" 2. Click on login button at the right corner 3. Keep both the field blank |  |  | Passed
33 |  |  |  | Checking if the data in password is masked | Should be masked | Found as per expectation | afrida09876 | 1. Goto the url "https://www.pickaboo.com/" 2. Click on login button at the right corner 3. Input value in password field and check if it is masked |  |  | Passed
34 |  |  |  | Checking login with wrong credentials in email and password fields | Should not allow user to login and display an error message | Found as per expectation | afd@xyz afridaxyz | 1. Goto the url "https://www.pickaboo.com/" 2. Click on login button at the right corner 3. Input invalid credentials in email and password field. |  |  | Passed
35 |  |  |  | Checking login with valid credentials in email and password field | Should allow user to login | Found as per expectation | afridaurmi@gmail.com afrida09876 | 1. Goto the url "https://www.pickaboo.com/" 2. Click on login button at the right corner 3. Input valid credentials in email and password field. |  |  | Passed
36 |  |  |  | Verifying "Forgot Password" functionality | Should sent an email or OTP number for recovery password | Found as per expectation | N/A | 1. Goto the url "https://www.pickaboo.com/" 2. Click on login button at the right corner 3. Clink on "Forgot Password" 4. Check email or phone for OTP number |  |  | Passed
37 |  |  |  | Verifying change the password link is sent to valid email address | Should be sent to valid email address | Found as per expectation | N/A | 1. Goto the url "https://www.pickaboo.com/" 2. Click on login button at the right corner 3. Clink on "Forgot Password" 4. Check email |  |  | Passed
38 |  |  |  | Verifying th efunctionality of "Set a new Pasword" | Should provide a new input for setting new password | Found as per expectation | N/A | 1. Goto the url "https://www.pickaboo.com/" 2. Click on login button at the right corner 3. Clink on "Forgot Password" 4. Check the registered email 5. Click on "Set up a new password" |  |  | Passed
39 |  |  |  | Checking "New Password" and "Confrim Password" are matched | Should give an error message | Found as per expectation | afrida09876 09876afrida | 1. Goto the url "https://www.pickaboo.com/" 2. Click on login button at the right corner 3. Clink on "Forgot Password" 4. Enter "new password" and "confirm password" with different value |  |  | Passed
40 |  |  |  | Verifying login with the new changed password | Should allow user to login | Found as per expectation | afridaurmi@gmail.com urmi123456 | 1. Goto the url "https://www.pickaboo.com/" 2. Click on login button at the right corner 3. Clink on "Forgot Password" 4. Enter "new password" 5. Click login |  |  | Passed
41 |  | Improvement Scopes |  | "Remember Me" checkbox should be selected according to user
42 |  |  |  | A maximum length of the password should be defined if user put the max value
43 |  |  |  | Place the 'Forgot your password link below the Password field

## Test Summary Report
Test Case Report
Project Name | Pickaboo (Online shoping platform)
Module Name | Customer Account
Feature Name | Sing up and Sign in
Test Case Version | 1
Written By | Afrida Rahman
Executed By | Afrida Rahman
Reviewed By | Ehsanul Alam Sabbir
Test Execution Report
Test Case | Pass | Fail | Not Executed | Out of Scope | Total TC
| 32 | 8 | 0 | 0 | 40
Limitations
Documents |  | Received |  | Useful
PRD |  | No |  | No
User Story |  | No |  | No
Testing Type in Scope |  | Description
Functional Testing |  | In order to determine whether the output satisfies the requirement, this kind of testing ignores the underlying commponents.
Integration Testing |  | Intregration testing is the process of testing all integrated modules to confirm their combined functionality after integration
Negetative Testing |  | Testing with a "Attitude to break" mentality by using incorrect data and invalid input
Usability Testing |  | Test application from user friendliness perspective
Browser Compatibility Testing |  | Web application undergo browser compatibility testing to make sure they can function on various operating systems and browser combinations
Boundary Value Testing |  | Each range has an uper and lower border, and testing is done using these boundary values
Risk Based Testing / Regression Testing |  | Highly critical functionality, which has the biggest influence on business and has a very high failure probability, is tested as part of risk based testing. Regression testing is the process of testing an application as a whole for changes made to any module or capability.

## Bug Report
Bug Reporting
Serial | 1
Issue | Entering blank at first position in firstname and lastname field
Reporting Steps | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Input space in first position on firstname and lastname
Environment | Production
Module | Sign up / Register
Priority
Severity
Expected Result | Should not accept the provided input
Actual Result | Not found as per expectation
Attachments | Entering blank at first position
Responsible QA | Afrida Rahman
Bug Reporting
Serial | 2
Issue | Entering blank at first position in firstname and lastname field
Reporting Steps | 1. Goto the url "https://www.pickaboo.com/" 2. Click on register button at the right corner 3. Input space in first position on firstname and lastname
Environment | Production
Module | Sign up / Register
Priority
Severity
Expected Result | Should not accept the provided input
Actual Result | Not found as per expectation
Attachments | Entering blank at first position
Responsible QA | Afrida Rahman

## Test Metrics
Test Metrics
Serial | Metrics | Description | Result
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | 80
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | 20
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A

## Recommendation
General Information
Test Stage | Unit Performance | Functionality Performance | Integration Acceptance | System Pilot | Interface
Date | 2023-12-01 |  | System Date (if applicable)
Tester | Afrida Rahman |  | Test Case No.
Test Case Description
Result | Pass Fail |  | Incident No. (if applicable)
Introduction
Requirement(s) to be Tested:
Roles and Responsibilites:
Setup Procedures:
Stop Procedures:
ENVIRONMENTAL NEEDS
Hardware:
Software:
Procedural Requirments:
TEST
Test Items and Features:
Input Specifications:
Procedural Steps:
Expected Results of Case:
ACTUAL RESULTS
Output Specifications: